## July 2025
QA Resources | Work this week | Learned this week | Plan for Next week | Reviewer Comments
Week - 21/07/2025 to 25/07/2025
Akash Singh | This week, I’m working on Endorsement and Cancellation transactions stories using the Postman API and validating them via the IMS UI. I am also engaged in the daily stand-up call with the Ascot QA team | I learned how to create these transactions via the IMS UI. While testing error handling through the API, I verified that when mandatory parameters are missing or empty in the request XML, the response XML should include the appropriate error messages. | This week, I will work on writing user stories for rewrite transactions, creating and executing test cases based on those stories, and producing supporting evidence.
Apoorva Gupta | This week, I worked on tickets SEQ-3386, SEQ-3370, SEQ-3320, and SEQ-3457, where I analyzed the requirements, designed relevant test cases, and executed them to validate the expected outcomes for the forms associated with the Businessowners Line of Business (LOB). | 1. Deepened understanding of the Businessowners Line of Business (LOB) and its associated forms. 2. Improved attention to detail by working with complex forms and multiple input combinations. 3. Gained experience in coordinating with developers, business analysts, and Clients while clarifying requirements or reporting issues. | Continue testing activities for the Businessowners Line of Business (LOB) forms: 1. Analyze newly developed or modified forms to understand their structure and business logic. 2. Design comprehensive test scenarios and cases covering all input fields, validations, and dynamic behaviors. 3. Execute test cases and validate the form functionality against the requirements and expected outcomes. 4. Log and track any defects identified during testing, and perform retesting after fixes.
Asis Kumar Saha | RTB-5465 : Change to Wording for CT BOP Pre 1965 and Post 1965 Rating to Pre 1995 in E-Comm and WINS Effective 8/1/25 Requirement is to amend risk type description for five risk for CT BOP product. Risk type denotes type of business. Each type of business have an unique code with description. To implement this we need to go for Table Update process then verify the result in both Ecomm and WINS using all transaction type. Completed Table Update process. Started WINS testing. During WINS testing found an issue and assigned the issue to the developer. | N/A | Will verify the particular issue. Will verify all transactions if anything else effected due to the fix. Will start Ecomm testing once development done.
Atul Saraswat | This week, I focused on the creation and review of Tosca scripts for stories TA-869 and TA-870, specifically related to the endorsement functionality. I also stayed engaged through daily stand-up calls and backlog grooming sessions. Additionally, I connected with Maggie, Chalaun, and the automation teams to align on progress and clarify requirements. | I learned about the process of document creation for the upcoming sprint, specifically how to evaluate what can realistically be committed to. Understanding the importance of a clear and thoughtful approach in planning has been key, as it helps set achievable goals and avoid overcommitment. | Next week, I aim to complete the development work for TA-869 and TA-870 and move toward initial testing or code review. I will also continue attending all sprint ceremonies and contribute to upcoming sprint planning discussions with a more structured and realistic approach.
Ayan Gupta | I worked on MA HOP Rate change which effective date is 10/05/2025. Done requirement analysis and Test case creation for company VM |  | I will continue working on MA HOP Rate change which effective date is 10/05/2025
Divyendu Shekhar | This week, I focused on analyzing user stories and requirements provided by the NIMBUS team. Working on ticket BPO- Polcy level Optional Coverages for Non Contracter. Additionally, I attended daily Scrum meetings to stay aligned with the team's progress and updates. | Learned Policy level Optional Covrages and work flow. Also learned how can map the requirment with the TC | I will continue analyzing the requirements and proceed with creating BOP (Business Owners Policy) policies. I plan to coordinate with the Business Analyst (BA) to gather updates related to application changes, particularly those involving coverage. I will also attend daily Scrum meetings to stay aligned with the team’s progress.
Kushal Khanra | Focused on the creation and customization of Quote Cover Letters for the E&S General Liability (GL) Program and the E&S Property (Prop) Program. This included aligning the cover letters with the specific requirements for each program, ensuring accurate display of coverage details, limits, and other critical data. Collaborated with internal teams to gather necessary inputs and incorporated dynamic tags to reflect coverage selections. Addressed formatting and alignment issues to enhance the professional presentation of the documents, ensuring they meet both client expectations and internal compliance standards. | Gained deeper insight into the structure and key components of Quote Cover Letters, particularly for the E&S General Liability and Property programs. This included understanding how to effectively communicate program-specific details, ensure compliance with regulatory standards, and tailor content to meet client and market expectations. Additionally, I enhanced my collaboration and document refinement skills through iterative feedback cycles with internal teams. | Next week, the focus will shift to developing the Quote Cover Letters for the Admitted Auto and Admitted Package programs. This will involve gathering program-specific requirements, identifying necessary dynamic tags, and ensuring the cover letters accurately reflect the coverage options, limits, and deductibles selected in the system. We will also ensure consistency in formatting and compliance with underwriting guidelines, while collaborating with relevant stakeholders to validate content accuracy and usability.
Mahavir.Routhan | For Amynta program-1, I have worked on 13 ADO board Features tickets in current week and overall 33 tickets so far in this month with multiple issues and multiple testing cycle when there is a new error after fix or defect not fixed. Co-ordinate with BA team for analysing the ticket from netrate and error files, testing of "Review production' tickets discussed new issues and resolution with internal team as well in the client call. Generate correction file from the client provided utility and analyse the defect has been fixed which is either under underwriter fixed or code fixed. Go through all comments in the ticket and if the correction file is not expected sent back it to grooming and discuss the same with BA team for further analysis. Attended regular internal BA co-ordination, Tickets discussion, Dev-BA co ordination, client meetings and one to one co-ordination with BA team. (https://docs.google.com/spreadsheets/d/1AHanQngy0tKw5lWvsi3QPP6LkKgaSIXbK1Sxd8MU9NE/edit?usp=sharing) (https://docs.google.com/spreadsheets/d/1X7Rp9Z6CHKg6mITCywPjDFn5JkFth6gR/edit?usp=sharing&ouid=112361677621571688871&rtpof=true&sd=true) | IMS - worksheet derived from netrate i.e those dollar amount which are not available in IMS UI but calculated in backend are available in the worksheet. | To do plan - To continue with Amynta project activities until all error policies will not fixed by focussing high dollar premium amount first and also go through the Rule engine develop by Manish team for program-1 to test it further.
Nadeem Khan | 1. Created a Status update sheet where updated the Backlog items from the emails. 2. Reviewed Backlog items from the Status Update sheet and also maintaining the same with all the tasks from the emails 3. Worked and analyzed 'Fortegra-Convelo Audit - Surplus Tax Calculations' related queries posted by Fortegra on Report. Consolidated the report with the solutions based on our analysis 4. Worked on preparing the consolidated list of Dec pages and Insuring Agreements for Auto, GL and Excess and shared the same with Eric Smith. 5. Working on setting up the Quote Cover Letter Template. 6. Created test policies data for 9 states and provided the details to Church Mutual to test Quick Solver and Bill It Now integration. | 1. Gained deeper insight into the structure and key components of Quote Cover Letters, particularly for the E&S General Liability and Property programs. 2. Gained Knowledge in understanding the set up and different variations in Surplus line taxes. 3. Understood the use of Dec pages and Insuring Agreements in Insurance for different LOBs like Auto, GL and Excess. 4. Learned to create Quote cover letters and their formatting. Also, learned to use tags in the QC | 1. Development of Quote cover letters for Admitted and Non-admitted programs. 2. Setting up Surplus line taxes in IMS. 3. Attending training on IMS and Bill It Now integration.
Pankaj Rawat | This Week I have analyzed and created test plan for RTB-6451 with Vinay, Requirment- MA HO rate change effective 10/05/2025 , INOW territory updates:NS, Workbook use new rate change , rate with new rates and territory codes after 10/05/2025 and before or prior 10/05/2025 workbook will use old rates | I Learned How to create test plan for HOP Line of Business in Guide-wire and the difference between new worksheet and Old worksheet. | To do plan - I will created Subsequent trasaction test plan for RTB-6451 with Vinay, Requirment- MA HO rate change effective 10/05/2025 , INOW territory updates:NS, Workbook use new rate change , rate with new rates and territory codes after 10/05/2025 and before or prior 10/05/2025 workbook will use old rates.
Pooja Kholiya | I did analysis of the user story AX- 5331 BOP FE- Building Level Coverages- Preferred Risk Pop-Up and AX-5464 BOP- Left Navigation Menu for Quote. Also created the test cases for AX-5464. |  | To do plan - To complete the test case of AX-5464 and execute them.
Praveen Kumar | 1. Creating the Quotes for Ezlynx Application 2. Creating the Polices for RI State PAP LOB 3. Creating test cases and teat data for RI state PAP LOB | I have learnt what an Agent Portal is and what the work of an agent is. How to create Test Cases in an effective way, how to create a dropdown for different fields in excel sheet. | Need to create 200 Quotes for Ezlynx CT state with PAP Lob, creating Policies for PAP RI and ME states in the Quincy Online application. Crating Test Cases and Test Data PAP.
Richa Trivedi | 1. Generated test data for Rhode Island (RI) Personal Auto Policy. 2. This included policy-level information and details for the driver and vehicle and for the personal driver assignment page. | Familiarized myself with the data combinations relevant to different vehicle classifications. | Need to work on more combination of fields and coverages that won't generate any error.
Rishab Tyagi | Worked on Re-Testing of the JIRA tickets raised during the Parallel Testing - Re-tested the fixed tickets in the UAT Environment and ensured that the current fixes do not hamper the existing functionality of the system. After restesting updated the Tickets Status in JIRA as per the Re-testing results. Once Ticket is deployed to PROD perform the Smoke Test on PROD which involves verifying the stability of key functionalities within the allowed constraints. Since we cannot create new records or modify existing data in the production environment, validated the deployed changes by performing a limited-scope sanity check. This includes checking the impacted modules or screens , primarily covering UI, navigation, access permissions, and any specific areas touched by the latest release. I attended Weekly Project Updates Meetings to Share the update and to stay aligned with the team's progress | Through this task, I developed a deeper understanding of the real-time QA lifecycle and the importance of maintaining system stability post-deployment. Key learnings include - Gained hands-on experience in UAT Re-testing, ensuring that fixes do not impact existing features.Improved proficiency in using JIRA for tracking ticket status and collaborating across teams.Understood the criticality of Smoke Testing in PROD, where validation needs to be precise and low-risk.Learned to identify and validate changes through limited-scope sanity checks, focusing on UI, navigation, permissions, and impacted modules.Enhanced my communication and collaboration skills by actively participating in weekly project update meetings, ensuring alignment with the broader team goals. | Take initiative in test case creation and optimization, especially for regression and sanity testing scenarios. Collaborate more with the dev and product teams to identify bugs early and improve release quality. Continue upskilling to make better defect reports
Sandip Banerjee | Create Policy at WINS - QA and UAT Env. for Guidewire Policy Center and Billing Center Integration Testing. |  | Create Policy Based on the Request from Policy Center and Billing Center Testing Team
Seshi Reddy | 1. Add policy placement types field in summary page for both new & renewal transaction in Convr 2. Add class of business field in summary page for both new & renewal transaction in Convr 3. Risk 360 page - Remove worksheet resources links. 4. Handle multiple rows of UM names form reference data when 1 product need to defaulted when auto population values in the following clearance page in Convr. 5. Manager referral - Ability to attach files within submission in Convr - Design 6. Defects Retesting | Learned about Air Integration SOV Calculation for all fields. | 1. Convr UI changes and rules when auto populating values in the following Clearance fields in Convr. 2. Defects Testing. 3. Continues to working on the Regtression Testing for every Sprint.
Srishti Lal | This week, I focused on analyzing user stories and requirements provided by the Beech Nuts team, which pertain to the data migration of BOP (Business Owners Policy) policies from the WINS system to the INOW platform. As part of this effort, I created BOP policies using the Agent Connection application and subsequently used the WINS system to edit policy information and perform rating activities. Additionally, I attended daily Scrum meetings to stay aligned with the team's progress and updates. | I gained an understanding of the ISO document—its purpose, structure, and how it is created. I also became familiar with the WINS system and its functionalities. Additionally, I learned how sprints are created and managed in Jira, providing insight into Agile project tracking and sprint planning. | I will continue analyzing the requirements and proceed with creating BOP (Business Owners Policy) policies. I plan to coordinate with the Business Analyst (BA) to gather updates related to application changes, particularly those involving coverage. Once the data migration is complete, I will review the mapping sheets and begin testing the migrated data for accuracy and completeness. I will also attend daily Scrum meetings to stay aligned with the team’s progress.
Subhajit Patra | I worked on MA Homeowners Rate change which effective date is 10/05/2025. Done requirement analysis and Test case creation for PL Rater and Singlepoint. |  | I will continue working on MA Homeowners Rate change which effective date is 10/05/2025
Updendar Reddy | 1. Got the requirements for My FPD sprint 11.2 2.I have prepared the test cases based on that and initiated the testing 3.I have completed the testing in QA and UAT environment for sprint 11.2 4.Will proceed for prod deployment after we got the approval from client |  | Waiting for requirements for sprint 11.3. Once got the requirements, need to create test cases for sprint 11.3
Vinay Kumar Reddy | I worked on RTB-6434 analysis the requirments Requirment is saying CT Homowners Rate change which effective date is 11/02/2025 before and on or after for comparing old and new rate books . Done requirement analysis and Test case creation for company VM AND RTB-5010 inflation guard reduce the 8 to 4% based on effective dates |  | writing the test plan for the same
Week - 28/07/2025 to 01/08/2025
Akash Singh | This week, I’m working on Endorsement and Cancellation transactions stories using the Postman API and validating them via the IMS UI. I am also engaged in the daily stand-up call with the Ascot QA team | I learned how to create these transactions via the IMS UI. While testing error handling through the API, I verified that when mandatory parameters are missing or empty in the request XML, the response XML should include the appropriate error messages. | This week, I will work on writing user stories for rewrite transactions, creating and executing test cases based on those stories, and producing supporting evidence.
Apoorva Gupta | This week, I worked on tickets SEQ-3304, SEQ-3301, and SEQ-3328, where I analyzed the requirements, designed relevant test cases, executed them, and raised the defects to validate the expected outcomes for the forms associated with the Businessowners Line of Business (LOB). | 1. Deepened understanding of the Businessowners Line of Business (LOB) and its associated forms. 2. Improved attention to detail by working with complex forms and multiple input combinations. 3. Gained experience in coordinating with developers, business analysts, and Clients while clarifying requirements or reporting issues. | Continue testing activities for the Businessowners Line of Business (LOB) forms: 1. Analyze newly developed or modified forms to understand their structure and business logic. 2. Design comprehensive test scenarios and cases covering all input fields, validations, and dynamic behaviors. 3. Execute test cases and validate the form functionality against the requirements and expected outcomes. 4. Log and track any defects identified during testing, and perform retesting after fixes.
Asis Kumar Saha | RTB-5465 : Change to Wording for CT BOP Pre 1965 and Post 1965 Rating to Pre 1995 in E-Comm and WINS Effective 8/1/25 Testing completed for WINS part including the defect which was identified during testing. | N/A | Analysing BOP Rate Change Requirement. (RTB-6425) RTB-5465 : Will start Ecomm testing once development done.
Atul Saraswat | This week, I focused on the creation and review of Tosca scripts for stories TA-869 and TA-870. Additionally, we performed a version upgrade of Tosca Commander, moving from 15.2 P1 to the 2024-25 version. Following the upgrade, we encountered a critical issue—we are currently unable to execute any scripts across the project. This issue has been escalated, and the entire team, including Chaluan, Maggie, and the Cognizant team, is actively investigating it in coordination with the Tosca support team to resolve it as soon as possible. | Gained experience in handling Tosca version upgrades and understanding their potential impact on existing automation scripts. Improved cross-team collaboration and incident management while troubleshooting critical issues post-upgrade, including coordinating with external support. | Continue working with the Tosca support team to resolve the script execution issue and aim to restore full automation functionality. Once the issue is resolved, focus on regression testing of updated scripts and resume scripting for any new stories in the sprint. Document the upgrade issue and resolution steps to prevent similar disruptions in future version changes.
Ayan Gupta | I was involved in the MA HOP rate change initiative, which is scheduled to take effect on October 10, 2025. I conducted a thorough analysis of the business and system requirements to ensure a clear understanding of the changes involved. Based on the requirements, I designed and documented detailed test cases to validate the functionality and compliance of the new rate structure. This work was is for Company NS (Northern Security) only |  | I will continue working on MA HOP Rate change which effective date is 10/05/2025 for QA Testing
Divyendu Shekhar | This week, I focused on analyzing user stories and requirements provided by the NIMBUS team. Working on ticket BPO- Polcy level Optional Coverages for Non Contracter. Additionally, I attended daily Scrum meetings to stay aligned with the team's progress and updates. (Part1 & 2 & 3 & 4) | Learned Policy level Optional Covrages and work flow. Also learned how can map the requirment with the TC | I will continue analyzing the requirements and proceed with creating BOP (Business Owners Policy) policies. I plan to coordinate with the Business Analyst (BA) to gather updates related to application changes, particularly those involving coverage. I will also attend daily Scrum meetings to stay aligned with the team’s progress.
Kushal Khanra | Focused on the creation and customization of Quote Cover Letters for the Admitted Auto and Admitted Package programs. This included aligning the cover letters with the specific requirements for each program, ensuring accurate display of coverage details, limits, and other critical data. Collaborated with internal teams to gather necessary inputs and incorporated dynamic tags to reflect coverage selections. Addressed formatting and alignment issues to enhance the professional presentation of the documents, ensuring they meet both client expectations and internal compliance standards. | Gained deeper insight into the structure and key components of Quote Cover Letters, particularly for the Admitted Auto and Admitted Package programs. This included understanding how to effectively communicate program-specific details, ensure compliance with regulatory standards, and tailor content to meet client and market expectations. Additionally, I enhanced my collaboration and document refinement skills through iterative feedback cycles with internal teams. | Next week, the focus will shift to developing the Quote Cover Letters for the E&S Package and Admitted Package programs. This will involve gathering program-specific requirements, identifying necessary dynamic tags, and ensuring the cover letters accurately reflect the coverage options, limits, and deductibles selected in the system. We will also ensure consistency in formatting and compliance with underwriting guidelines, while collaborating with relevant stakeholders to validate content accuracy and usability.
Mahavir.Routhan | For Amynta program-1, I have worked on 15 ADO board Features tickets having total dollar amount of $545,245 in which one ticket with -ve $9,911 and one having $0. Co-ordinate with BA team for analysing the ticket from netrate and error files, testing of "Review production' tickets discussed new issues and resolution with internal team as well in the client call. Generate correction file from the client provided utility and analyse the defect has been fixed which is either under underwriter fixed or code fixed. Go through all comments in the ticket and if the correction file is not expected sent back it to grooming and discuss the same with BA team for further analysis or blocked if issue still persist. Attended regular internal BA co-ordination, Tickets discussion, Dev-BA co ordination, client meetings and one to one co-ordination with BA team. | Uncancel feature of client provided utility where we use the uncancel if the amount is booked for the subsequent error transactions | To do plan - To continue with Amynta project activities until all error policies will not fixed by focussing high dollar premium amount first.
Nadeem Khan | 1. Udpating status sheet where updated the Backlog items from the emails. 2. Reviewed Backlog items from the Status Update sheet and also maintaining the same with all the tasks from the emails 3. Working on setting up the Quote Cover Letter Template. 4. Working on reviewing the Surplus Line taxes configuration in IMS by Vertafore. New tax logic requires to be implemented as per the latest update from Eric Smith. 5. Updating Surplus Line new taxes logic as per the latest update for HAB GL Program. | 1. Gained deeper insight into the structure and key components of Quote Cover Letters, particularly for the E&S General Liability and Property programs. 2. Gained Knowledge in understanding the set up and different variations in Surplus line taxes. 3. Learned to create Quote cover letters and their formatting. Also, learned to use tags in the QC | 1. Development of Quote cover letters for Admitted and Non-admitted programs. 2. Setting up Surplus line taxes in IMS.
Pankaj Rawat | I worked on RTB-6434-(3 Requirements) test planning is completed Requirment is saying CT Homowners Rate change which effective date is 11/02/2025 before and on or after for comparing old and new rate books . Done requirement analysis and Test case creation for company VM | I Learned How to create test plan for HOP Line of Business in Guide-wire and the difference between new worksheet and Old worksheet. | Requirement is in deployment by developer team , if it will deployed then work on execution
Praveen Kumar | 1. Creating the Quotes for Ezlynx Application CT States 2. Creating the Polices for CT State PAP LOB 3. Creating test cases and test data for Automation 4. Running the Automation for PAP RI State and sharing the results with Shubham | I have learned about how to run the Automation for the Quincy project and how to fix the errors in the Input sheet if any | Need to create 200 Quotes for Ezlynx RI state with PAP Lob, creating Policies for PAP CT states in the Quincy Online application. Running Automation for PAP RI State.
Pooja Kholiya | Execution of test cases of user story AX-5464 BOP- Left Navigation Menu for Quote. Also raised the 2 defects from this story, had discussion on those defects one defects was change to user stories( For the prompt pop up for unsaved data while navigating to another tab). One is being fixed( the defect was for color coding of the current tab). |  | Will go through the user stories and creating test cases for the same. Meanwhile if any story comes for testing will analyse and execute the test cases.
Richa Trivedi | 1. Working on test data creation for the Maine (ME) Personal Auto Policy (PAP). 2. Executing the test cases based on 2 Driver & 2 Vehicle combinations. 3. Finding and reporting the defects in the system. | Familiarized myself with the data combinations relevant to different vehicle classifications. | Need to work on more combination of fields and coverages that won't generate any error.
Rishab Tyagi | Worked on Re-Testing of the JIRA tickets raised during the Parallel Testing - Re-tested the fixed tickets in the UAT Environment and ensured that the current fixes do not hamper the existing functionality of the system. After restesting updated the Tickets Status in JIRA as per the Re-testing results. Once Ticket is deployed to PROD perform the Smoke Test on PROD which involves verifying the stability of key functionalities within the allowed constraints. Since we cannot create new records or modify existing data in the production environment, validated the deployed changes by performing a limited-scope sanity check. This includes checking the impacted modules or screens , primarily covering UI, navigation, access permissions, and any specific areas touched by the latest release. I attended Weekly Project Updates Meetings to Share the update and to stay aligned with the team's progress | Through this task, I developed a deeper understanding of the real-time QA lifecycle and the importance of maintaining system stability post-deployment. Key learnings include - Gained hands-on experience in UAT Re-testing, ensuring that fixes do not impact existing features.Improved proficiency in using JIRA for tracking ticket status and collaborating across teams.Understood the criticality of Smoke Testing in PROD, where validation needs to be precise and low-risk.Learned to identify and validate changes through limited-scope sanity checks, focusing on UI, navigation, permissions, and impacted modules.Enhanced my communication and collaboration skills by actively participating in weekly project update meetings, ensuring alignment with the broader team goals. | Take initiative in test case creation and optimization, especially for regression and sanity testing scenarios. Collaborate more with the dev and product teams to identify bugs early and improve release quality. Continue upskilling to make better defect reports
Sandip Banerjee | Create Policy at WINS - QA and UAT Env. for Guidewire Policy Center and Billing Center Integration Testing. |  | Create Policy Based on the Request from Policy Center and Billing Center Testing Team
Seshi Reddy | 1. Sprint -31-E2E Regression Testing 2. Defects Retesting for S-31. 3. Convr UI changes and rules when auto populating values in the following Clearance fields in Convr-Design 4. Add dropdown value Side A in Policy Placement type fiend in Convr-Design |  | 1. Manager Referral - Ability to Attach Files Outside of UWWB-Design 2. AI Training - Enhance Clearance extraction of Producer fields with Training of email content - email body and attachments-Design 3. Change the Default for Browse Files to Archive-Execution 4. Convr to Outlook - Add Ability to Save Email as a 'DRAFT' in Convr-Execution 5. Defects Testing for S-32. 6. Continues to working on the Regtression Testing for every Sprint.
Srishti Lal | This week, I analyzed user stories for Sprint 2, which focused on data migration activities. I reviewed the premium-bearing coverages available in both the INOW and WINS systems to understand their mapping and consistency and created policies. Additionally, I attended daily Scrum calls and participated in sprint planning meetings to stay aligned with the team's objectives. | This week, I gained an understanding of CUP (Commercial Umbrella Policy) policies, including their structure and how they function within the application. | Next week, I will focus on analyzing user stories and gaining an understanding of the new updates made for BOP (Business Owners Policy) and CUP (Commercial Umbrella Policy) in the INOW system. I will also attend daily stand-up meetings to stay aligned with the team’s updates and progress.
Subhajit Patra | I worked on MA Homowners Rate change which effective date is 10/05/2025. Done requirement analysis and Test case creation for Appian part. I am testing PL Rater and Singlepoint scenarios. |  | I will continue working on MA Homeowners Rate change which effective date is 10/05/2025
Upendar Reddy | 1. Waiting for client approval for production deployment 2.Once got approval I will test the production for My FPD sprint 11.2 3.Tested the sprint 11.2 requirements on production | I gained a good understanding of User roles and permissions in My FPD application. Found a timezone issue in audit trail when randomly testing by changing the timezones, decided to include this scenario while testing in future sprints | 1. Got the requirements for sprint 12 2. Started writing the test cases based on that requirements
Vinay Kumar Reddy | I worked on RTB-6434 ( 3 child req form main req ) test planning is completed Requirment is saying CT Homowners Rate change which effective date is 11/02/2025 before and on or after for comparing old and new rate books . Done requirement analysis and Test case creation for company VM |  | once story is deployed will start execution for the same

## July 28- Aug1 2025
QA Resources | Work this week | Learned this week | Plan for Next week | Reviewer Comments
Akash Singh | This week, I’m working on Rewrite and Reinstatement transactions stories using the Postman API and validating them via the IMS UI. I am also engaged in the daily stand-up call with the Ascot QA team | I learned how to create these transactions via the IMS UI. While testing error handling through the API, I verified that when mandatory parameters are missing or empty in the request XML, the response XML should include the appropriate error messages. | This week, I will work on writing user stories for Unbind transactions, creating and executing test cases based on those stories, and producing supporting evidence.
Apoorva Gupta | This week, I worked on tickets SEQ-3304, SEQ-3301, and SEQ-3328, where I analyzed the requirements, designed relevant test cases, executed them, and raised the defects to validate the expected outcomes for the forms associated with the Businessowners Line of Business (LOB). | 1. Deepened understanding of the Businessowners Line of Business (LOB) and its associated forms. 2. Improved attention to detail by working with complex forms and multiple input combinations. 3. Gained experience in coordinating with developers, business analysts, and Clients while clarifying requirements or reporting issues. | Continue testing activities for the Businessowners Line of Business (LOB) forms: 1. Analyze newly developed or modified forms to understand their structure and business logic. 2. Design comprehensive test scenarios and cases covering all input fields, validations, and dynamic behaviors. 3. Execute test cases and validate the form functionality against the requirements and expected outcomes. 4. Log and track any defects identified during testing, and perform retesting after fixes.
Asis Kumar Saha | RTB-5465 : Change to Wording for CT BOP Pre 1965 and Post 1965 Rating to Pre 1995 in E-Comm and WINS Effective 8/1/25 Testing completed for WINS part including the defect which was identified during testing. | N/A | Analysing BOP Rate Change Requirement. (RTB-6425) RTB-5465 : Will start Ecomm testing once development done.
Atul Saraswat | This week, I focused on the creation and review of Tosca scripts for stories TA-869 and TA-870. Additionally, we performed a version upgrade of Tosca Commander, moving from 15.2 P1 to the 2024-25 version. Following the upgrade, we encountered a critical issue—we are currently unable to execute any scripts across the project. This issue has been escalated, and the entire team, including Chaluan, Maggie, and the Cognizant team, is actively investigating it in coordination with the Tosca support team to resolve it as soon as possible. | Gained experience in handling Tosca version upgrades and understanding their potential impact on existing automation scripts. Improved cross-team collaboration and incident management while troubleshooting critical issues post-upgrade, including coordinating with external support. | Continue working with the Tosca support team to resolve the script execution issue and aim to restore full automation functionality. Once the issue is resolved, focus on regression testing of updated scripts and resume scripting for any new stories in the sprint. Document the upgrade issue and resolution steps to prevent similar disruptions in future version changes.
Ayan Gupta | I worked on MA HOP Rate change which effective date is 10/05/2025. Done requirement analysis and Test case creation for company NS |  | I will continue working on MA HOP Rate change which effective date is 10/05/2025 for QA Testing
Divyendu Shekhar | This week, I focused on analyzing user stories and requirements provided by the NIMBUS team. Working on ticket BPO- Polcy level Optional Coverages for Non Contracter. Additionally, I attended daily Scrum meetings to stay aligned with the team's progress and updates. (Part1 & 2 & 3 & 4) | Learned Policy level Optional Covrages and work flow. Also learned how can map the requirment with the TC | I will continue analyzing the requirements and proceed with creating BOP (Business Owners Policy) policies. I plan to coordinate with the Business Analyst (BA) to gather updates related to application changes, particularly those involving coverage. I will also attend daily Scrum meetings to stay aligned with the team’s progress.
Kushal Khanra | Focused on the creation and customization of Quote Cover Letters for the Admitted Auto and Admitted Package programs. This included aligning the cover letters with the specific requirements for each program, ensuring accurate display of coverage details, limits, and other critical data. Collaborated with internal teams to gather necessary inputs and incorporated dynamic tags to reflect coverage selections. Addressed formatting and alignment issues to enhance the professional presentation of the documents, ensuring they meet both client expectations and internal compliance standards. | Gained deeper insight into the structure and key components of Quote Cover Letters, particularly for the Admitted Auto and Admitted Package programs. This included understanding how to effectively communicate program-specific details, ensure compliance with regulatory standards, and tailor content to meet client and market expectations. Additionally, I enhanced my collaboration and document refinement skills through iterative feedback cycles with internal teams. | Next week, the focus will shift to developing the Quote Cover Letters for the E&S Package and Admitted Package programs. This will involve gathering program-specific requirements, identifying necessary dynamic tags, and ensuring the cover letters accurately reflect the coverage options, limits, and deductibles selected in the system. We will also ensure consistency in formatting and compliance with underwriting guidelines, while collaborating with relevant stakeholders to validate content accuracy and usability.
Mahavir.Routhan | For Amynta program-1, I have worked on 15 ADO board Features tickets having total dollar amount of $545,245 in which one ticket with -ve $9,911 and one having $0. Co-ordinate with BA team for analysing the ticket from netrate and error files, testing of "Review production' tickets discussed new issues and resolution with internal team as well in the client call. Generate correction file from the client provided utility and analyse the defect has been fixed which is either under underwriter fixed or code fixed. Go through all comments in the ticket and if the correction file is not expected sent back it to grooming and discuss the same with BA team for further analysis or blocked if issue still persist. Attended regular internal BA co-ordination, Tickets discussion, Dev-BA co ordination, client meetings and one to one co-ordination with BA team. | Uncancel feature of client provided utility where we use the uncancel if the amount is booked for the subsequent error transactions | To do plan - To continue with Amynta project activities until all error policies will not fixed by focussing high dollar premium amount first.
Nadeem Khan | 1. Udpating status sheet where updated the Backlog items from the emails. 2. Reviewed Backlog items from the Status Update sheet and also maintaining the same with all the tasks from the emails 3. Working on setting up the Quote Cover Letter Template. 4. Working on reviewing the Surplus Line taxes configuration in IMS by Vertafore. New tax logic requires to be implemented as per the latest update from Eric Smith. 5. Updating Surplus Line new taxes logic as per the latest update for HAB GL Program. | 1. Gained deeper insight into the structure and key components of Quote Cover Letters, particularly for the E&S General Liability and Property programs. 2. Gained Knowledge in understanding the set up and different variations in Surplus line taxes. 3. Learned to create Quote cover letters and their formatting. Also, learned to use tags in the QC | 1. Development of Quote cover letters for Admitted and Non-admitted programs. 2. Setting up Surplus line taxes in IMS.
Pankaj Rawat | I worked on RTB-6434-(3 Requirements) test planning is completed Requirment is saying CT Homowners Rate change which effective date is 11/02/2025 before and on or after for comparing old and new rate books . Done requirement analysis and Test case creation for company VM | I Learned How to create test plan for HOP Line of Business in Guide-wire and the difference between new worksheet and Old worksheet. | Requirement is in deployment by developer team , if it will deployed then work on execution
Praveen Kumar | 1. Creating the Quotes for Ezlynx Application CT States 2. Creating the Polices for CT State PAP LOB 3. Creating test cases and test data for Automation 4. Running the Automation for PAP RI State and sharing the results with Shubham | I have learned about how to run the Automation for the Quincy project and how to fix the errors in the Input sheet if any | Need to create 200 Quotes for Ezlynx RI state with PAP Lob, creating Policies for PAP CT states in the Quincy Online application. Running Automation for PAP RI State.
Pooja Kholiya | Execution of test cases of user story AX-5464 BOP- Left Navigation Menu for Quote. Also raised the 2 defects from this story, had discussion on those defects one defects was change to user stories( For the prompt pop up for unsaved data while navigating to another tab). One is being fixed( the defect was for color coding of the current tab). |  | Will go through the user stories and creating test cases for the same. Meanwhile if any story comes for testing will analyse and execute the test cases.
Richa Trivedi | 1. Working on test data creation for the Maine (ME) Personal Auto Policy (PAP). 2. Executing the test cases based on 2 Driver & 2 Vehicle combinations. 3. Finding and reporting the defects in the system. | Familiarized myself with the data combinations relevant to different vehicle classifications. | Need to work on more combination of fields and coverages that won't generate any error.
Rishab Tyagi | Worked on Re-Testing of the JIRA tickets raised during the Parallel Testing - Re-tested the fixed tickets in the UAT Environment and ensured that the current fixes do not hamper the existing functionality of the system. After restesting updated the Tickets Status in JIRA as per the Re-testing results. Once Ticket is deployed to PROD perform the Smoke Test on PROD which involves verifying the stability of key functionalities within the allowed constraints. Since we cannot create new records or modify existing data in the production environment, validated the deployed changes by performing a limited-scope sanity check. This includes checking the impacted modules or screens , primarily covering UI, navigation, access permissions, and any specific areas touched by the latest release. I attended Weekly Project Updates Meetings to Share the update and to stay aligned with the team's progress | Through this task, I developed a deeper understanding of the real-time QA lifecycle and the importance of maintaining system stability post-deployment. Key learnings include - Gained hands-on experience in UAT Re-testing, ensuring that fixes do not impact existing features.Improved proficiency in using JIRA for tracking ticket status and collaborating across teams.Understood the criticality of Smoke Testing in PROD, where validation needs to be precise and low-risk.Learned to identify and validate changes through limited-scope sanity checks, focusing on UI, navigation, permissions, and impacted modules.Enhanced my communication and collaboration skills by actively participating in weekly project update meetings, ensuring alignment with the broader team goals. | Take initiative in test case creation and optimization, especially for regression and sanity testing scenarios. Collaborate more with the dev and product teams to identify bugs early and improve release quality. Continue upskilling to make better defect reports
Sandip Banerjee | Create Policy at WINS - QA and UAT Env. for Guidewire Policy Center and Billing Center Integration Testing. |  | Create Policy Based on the Request from Policy Center and Billing Center Testing Team
Seshi Reddy | 1. Sprint -31-E2E Regression Testing 2. Defects Retesting for S-31. 3. Convr UI changes and rules when auto populating values in the following Clearance fields in Convr-Design 4. Add dropdown value Side A in Policy Placement type fiend in Convr-Design |  | 1. Manager Referral - Ability to Attach Files Outside of UWWB-Design 2. AI Training - Enhance Clearance extraction of Producer fields with Training of email content - email body and attachments-Design 3. Change the Default for Browse Files to Archive-Execution 4. Convr to Outlook - Add Ability to Save Email as a 'DRAFT' in Convr-Execution 5. Defects Testing for S-32. 6. Continues to working on the Regtression Testing for every Sprint.
Srishti Lal | This week, I analyzed user stories for Sprint 2, which focused on data migration activities. I reviewed the premium-bearing coverages available in both the INOW and WINS systems to understand their mapping and consistency and created policies. Additionally, I attended daily Scrum calls and participated in sprint planning meetings to stay aligned with the team's objectives. | This week, I gained an understanding of CUP (Commercial Umbrella Policy) policies, including their structure and how they function within the application. | Next week, I will focus on analyzing user stories and gaining an understanding of the new updates made for BOP (Business Owners Policy) and CUP (Commercial Umbrella Policy) in the INOW system. I will also attend daily stand-up meetings to stay aligned with the team’s updates and progress.
Subhajit Patra | I worked on MA Homowners Rate change which effective date is 10/05/2025. Done requirement analysis and Test case creation for Appian part. I am testing PL Rater and Singlepoint scenarios. |  | I will continue working on MA Homeowners Rate change which effective date is 10/05/2025
Upendar Reddy | 1. Waiting for client approval for production deployment 2.Once got approval I will test the production for My FPD sprint 11.2 3.Tested the sprint 11.2 requirements on production | I gained a good understanding of User roles and permissions in My FPD application. Found a timezone issue in audit trail when randomly testing by changing the timezones, decided to include this scenario while testing in future sprints | 1. Got the requirements for sprint 12 2. Started writing the test cases based on that requirements
Vinay Kumar Reddy | I worked on RTB-6434 ( 3 child req form main req ) test planning is completed Requirment is saying CT Homowners Rate change which effective date is 11/02/2025 before and on or after for comparing old and new rate books . Done requirement analysis and Test case creation for company VM |  | once story is deployed will start execution for the same

## Sep 29- Oct 3 2025
QA Resources | Client Name | Project Name | Work this week | Learned this week | Future work plans | Reviewer Comments
Akash Singh | Ascot,Quincy | Ascot, Quincy | Ascot – Continue support for integration team queries, and if anything comes up, investigate the same and create an Evidence doc for the same Quincy – Continue creating test data for the RI state. |  | Ascot – Continue To work in sprint 5 and planning for sprint 6
Apoorva Gupta | Vermont | VM- Wired | This week, I worked on tickets SEQ-3447, SEQ-3547, SEQ-3376, SEQ-3451, SEQ-3678, and SEQ-3542, where I analyzed the requirements, designed relevant test cases, executed them, and raised the defects to validate the expected outcomes for the forms associated with the Businessowners Line of Business (LOB). | N/A | Continue testing activities for the Businessowners Line of Business (LOB) forms: 1. Analyze newly developed or modified forms to understand their structure and business logic. 2. Design comprehensive test scenarios and cases covering all input fields, validations, and dynamic behaviors. 3. Execute test cases and validate the form functionality against the requirements and expected outcomes. 4. Log and track any defects identified during testing, and perform retesting after fixes.
Asis Kumar Saha | Vermont | Run The Business | RTB-6819 : VM - Add MA HO Flood Disclosure | N/A | RTB-6820 : NS - Add MA HO Flood Disclosure
Atul Saraswat | Vermont | VM-Tosca Automation | This week, I worked on creating the execution list for stories 1004 and 1005, which are related to the DFA regression testing for the RI and CT states. Additionally, as per Chalaun’s request, we re-executed all the scripts for the Ping update across different environments. I have successfully completed four stories, which included a total of 20 scripts, and I am currently in the process of re-executing them to ensure all updates are validated properly. | N/A | In the upcoming week, I will continue my work on the DFA regression story for the ME state and extend the testing to cover other states as part of the ongoing DFA regression cycle. The focus will be on completing the execution list, validating results, and ensuring that all automated scripts run smoothly across environments without any discrepancies.
Ayan Gupta | Vermont | Run The Business | RTB - 6805 - Test Only - MA PAP Rate Change Effective 1/1/2026 - Obtain a Quote Through VM Front End - Test Case Creation RTB - 6804 - Test Only - MA PAP Rate Change effective 1/1/2026 - Obtain a Quote Through SinglePoint - Test Case Creation |  | RTB - 6805 - Test Only - MA PAP Rate Change Effective 1/1/2026 - Obtain a Quote Through VM Front End - Test Case Creation RTB - 6804 - Test Only - MA PAP Rate Change effective 1/1/2026 - Obtain a Quote Through SinglePoint - Test Case Execution
Divyendu Shekhar | Vermont | Nimbus
Kushal Khanra | Convelo | FRI E&S Package & Admitted Package | Worked on editing the Quote Cover Letter for the Admitted Auto program as per UW's comments. Also Provided assistance on defect management for the Client. | Gained knowledge on how the forms are build and implemented in the IMS system. Gained knowledge about the Taxes and Fees that are applied in US on E&S Programs Explored the basics of Insurance domain - Learned about the Flow of a policy Quote in Insurance.. | Focusing on providing assistance to Client as required related to the maintainenct of the Convelo Programs.
Mahavir.Routhan | Internal | Quincy IMS Security Testing | Co-ordinate with Quincy Test, Dev and automation team to understand the process and gaps. Going through IMS training videos shared by Teena, Internal co-ordination for Security Testing related training and going though the fundamentals, attended QA internal status meetings and Security testing topics discussions | Go through Basecamp video of IMS Training Session - UI Crash Course for Devs Understand the concept of IPv4, IPV6, IIS etc.
Nadeem Khan | Convelo | FRI Package Fortegra DNO FI Non Profit Support HAB GL KMG IMS
Pankaj Rawat | Vermont | INOW UPGRADE to KUFRI | I am analyzing the requirement RTB-6123, FIXED web path exception when updating an existing attachment or note caused a validation error , UI Fixed advance option with a new attachment no longer "hides" but retains it's state if there is validation error | I learned about the functionality of Quick access menu | I will execute the requirement RTB-6123
Pooja Kholiya | Vermont | Nimbus | I am analysing and creating the test cases for the following tickets: AX-6487- Policy level coverage- Storm Deductible Type option being added. AX- 6273- Non-Constructor Policy level UW questions. | NA | Will execute the test cases once deployed.
Praveen Kumar | Quincy | Agency Port Interfaces (Ezlynx) & Rating Rewrite with Python | 1. Creating the Quotes for the Ezlynx Application for PAP ME States 2. Correcting test cases and test data for Automation 1D and 1V | I have understood how to estimate the efforts and time to complete the task | Recreating the new Quotes for Ezlynx PAP testing. Need to create 135 Quotes for Ezlynx ME state with PAP Lob,
Richa Trivedi | Quincy | Rating Rewrite with Python | 1. I have created test data for PAP RI(3 drivers & 1 vehicle) covering 50 unique scenarios for automation testing. 2. I have analysed the defects for PAP RI(1D2V, 2D1V, 2D2V and 3D1V) and shared the correct data to the Automation team. 3. I have created test data for PAP RI(4 drivers & 6 vehicle) covering 25 unique scenarios for automation testing. | I discovered the issues that were causing the automation to fail. | Will work on correcting any data-related issues for any scenarios and start working on CT state
Rishab Tyagi | Fortegra | Fortegra-Motorclubs
Sandip Banerjee | MSIG | Guidewire Implementation | 1. Create Policy at WINS - QA for Guidewire Policy Center and Billing Center Integration Testing which are rquire for WINS to CC for Non-WCA Policy. |  | Based on the Request from Policy Center and Billing Center Testing Team
Seshi Reddy | MSIG | Underwriting Workbench | 1. UI Updates on all Forms will reflect on Summary and Clearance on Small Save (Forms save button) - immediately on save - PART 2_Design 2. UI Updates on all Forms will reflect on Summary and Clearance on Small Save (Forms save button) - immediately on save - PART 2_Execution 3. Schema updates for all Forms –Updated values are getting changed to old values when user advance the stage_Defect Testing 4. UWWB Sprint 35 end to end regression testing. |  | Automation Learing and process. Claim creation in CC.
Srishti Lal | Vermont | Beech Nuts | 1. Completed RTB- 6148 i.e. While creating new loss notice user can navigate to different nodes available at the left panel and access it without getting web path error. 2. Worked on the requirement analysis and test case creation for RTB-6094 I.E related to password format for different uses as Inow will not allow users to have a common password.It will display error message if the password does not meet the format provided. 3. Reviewed a few migrated BOP policies from WINS to INOW. 4. Reported qurey regarding RTB-RTB-6327 i.e subscription list delivery method dropdown options. |  | 1. Work on RTB- 6352 related to subscription list delivery method it should retain its value even if one of the delivery method is changed. 2.Work on RTB- 6115 i.e. "INOV upgrade: in User Maintenance, for Company Claims or Provider User Types, the Provider search option Only show providers whose territory matches this claim has been removed. 3. Complete Execution RTB-6094 i.e. related to password format for different uses as Inow will not allow users to have a common password.It will display error message if the password does not meet the format provided.
Subhajit Patra | Vermont | Run The Business | Completed test plan preparation for RTB-6803[MA PAP Rate Change] |  | I will continue working on RTB-6803[ MA PAP Rate Change-INOW Portion.]
Upendar Reddy | Field Pros Direct | Adjuster Locator | 1.The QA testing for Sprint 13 has been successfully completed 2.All identified issues during the testing phase were raised, tracked, and resolved by the development team. 3.A Total of 36 issues were reported during testing 4.Following the resolution, Sprint 13 has been deployed to the UAT environment. 5.I will now proceed with UAT testing to ensure all functionalities are working as expected |  | 1. I will complete the UAT testing today 2.Waiting for client approval to move to prod
Vinay | PIT CREW | VERMONT | Test cases in progress and test execution is completed for below stories the below stories RTB-6163 -Test plan is inprogress RTB-6165 - reversal claim loss summary options RTB-6161-Statement account method is not being roll back RTB-6154-Data entry error is claim page RTB-6141-sort by work date -Rised effect RTB-6862(Execution) |  | Will work on Inow upgrades Stories
Ankit Kumar | Agent AI POC & Quincy | RPA | 1. Go through the Test Data Generator code for Quincy and AQ to understand its logic. 2. Worked on fixing the issue with generating Test Case Numbers and Transactions. 3. Analyze workbook structure & confirm rules in Quincy bots. | Learned how to use Python libraries like Flask, pandas, and Faker to build a test data generator that creates Excel files with dynamic IDs and realistic sample data. | Continue to work on the development of Quincy bots.
Kamakshi Tewari | Agent AI POC | RPA | Created poc ready code for generating test data as per user's requirement. | I learned deep structural formatting using python for the POC build up. | Continuing to work on formatting fields and creating chat bot.
Mudita Jain | Loss Run & Agent AI POC | RPA | Exctracted the data from the provides files and added few activities in the build up process & Initiated development. | I worked on extracting data and learnt formatting structure of fields using python. | Continuing to work on Data Extraction of Loss Run Files and Agent AI POC.
Shubham Dhyani | Quincy | Quincy Automation PAP | 1. Completed 50 test sets for 1d1v for RI 2. Completed Testing for corrected data for 2d2v, 3d1v. 3. Tested 25 test sets for 4d6v. | I explored Power Apps | I will contnue to Test for New Business and subsequent transactions for ME and CT state and update the scripts if any change occurs.
Susmita Chakraborty | Merchants Insurance Group Inc. | Dot Net Quote and Issue process | 1. Created automation for the WC and CAP Quoting and Issuing process. 2. Updated selector for all the DotNet scenarios across all LOBs. | I learned how to issue a binder after the quote creation process. | I am continuing to build automation for the Quote and Issue process for different LOB's.